Bukrah Foundation

What We Need from Abu Hani

Masar Youth Center, project BF-MSAR-001. Prepared 10/11/2026.

The rule behind every item: Bukrah pays for what it can show on paper. Masar's own documents must say what was bought, from whom, for how much, and who received it. Nothing else changes.

1. Now, by 10/18

| What | Why |
| --- | --- |
| One signed debt statement with only what Masar truly believes is owed. Each line comes with the supplier's statement and the receipt. A line without paper comes off. | Masar gave three different numbers: 30,600 on 10/02, 18,000 before that, and on 10/05 Abu Hani told Dr. Ahlia nothing is owed beyond October water, already paid. |
| Straight answers to three questions: where the basket money booked on receipts 00158 and 00159 went, whether September water is paid, and why board pay was added. | Masar's own receipts book 19,509 to baskets against one 6,000 invoice, and 10,000 to September water. Board pay was never agreed. |

2. Every water delivery, from the next one

| What | Why |
| --- | --- |
| The daily water log, BF-T11, signed by hand by the camp delegate on the day, with a photo of the tanker plate while it unloads. | The October log we received was one typed page with typed names, signed by the supplier himself. It proves nothing. |

3. Every purchase and every distribution, from 10/19

| What | Why |
| --- | --- |
| At the purchase: photos and video of the goods, the quantity, and the seller. Raw files, sent within 24 hours, with the seller's invoice. | Rule BF-R03 applies to every partner from 10/19. It is what the lawyer and the accountant need, and what donors see. |
| At the distribution: photos and video, with the photo log BF-T14 filled in. | Shows the goods reached the people they were bought for. |

4. Once

| What | Why |
| --- | --- |
| For every person on the vetting form: the social media declaration BF-T24, and a fresh signature with the real date of signing. | United States law requires Bukrah to review every name it pays. Same for all partners. |

5. Always

- No work starts before written approval from Mohammad or Dr. Ahlia. Filling the request form is not approval.

- A live video call once a week during a distribution. Two minutes.

- All money requests and all papers go to Mohammad, and Mohammad answers.

- In return: an answer within three working days on any complete file, and a transfer that does not wait once the papers are complete.